## Timeline and Human Resources
Project Web-Application OpenRead
LA06 |  |  | Human Resources
NIM | Name |  | PIC | Name
2201734814 | Anthony Gilrandy Theo |  | Project Manager (PM) | Steven
2201740546 | Dewi Puspita Tanurezal |  | Modelling (Designer) | Dewi
2201755131 | Devita |  | Software Analyst (SA) | Devita
2201852132 | Steven |  | Developer Backend (Dev BE) | Anthony
|  |  | Developer Frontend (Dev FE) | Devita
Steven
|  |  | Quality Assurance | Bu Sonya
TIMELINE
Task | Sub Task | PIC | September |  | October |  |  |  | November |  |  |  | December |  |  |  | January
|  |  | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
Requirement Engineering | Research | PM | bar: September 4 to October 1
| Questionnaire | PM | bar: October 1
| SRS | PM | bar: October 2 to October 3; November 2 to December 1
Analisis | Process Analayis | SA | bar: November 2 to November 3
| System's Diagram | SA | bar: November 2 to November 3
Modeling | User Interfaces | Designer | bar: November 3 to December 1
Backend Development | Initialize Project | Dev BE | bar: December 3
| Integration | Dev BE | bar: January 2
Frontend Development | Home Page | Dev FE | bar: December 3 to December 4
| Navigation Bar | Dev FE | bar: December 4
| Story Pages | Dev FE | bar: December 4 to January 1
| Profile Pages | Dev FE | bar: December 4 to January 1
Testing Integration | Testing | QA | bar: January 2

## Project Cost
Cost (Technical)
Component | Detail | Description | Qty | Price |  | Subtotal
Hardware | Laptop | Laptops that are required for the project | 4 | 10000000 |  | 40000000
Software | Visual Studio Code | For Frontend Development |  | 0 |  | 0
| php | Programming Language for web development |  | 0 |  | 0
| mySQL | Database Management System for database needed for storing user credentials and story |  | 0 |  | 0
| Photoshop | Adobe Photoshop needed for graphical design (1 month) | 1 | 150000 |  | 150000
| Microsoft Office | For Documents (Word and Excel) | 1 | 350000 |  | 350000
Human Resource | Project Manager | Planning, overseeing, and leading the whole process of the projects | 1 | 100000000 |  | 100000000
| Designer | Design the interfaces for the application | 1 | 5000000 |  | 5000000
| Backend | Backend Developer (Responsible for the server-side logic) | 1 | 20000000 |  | 20000000
| Frontend | Frontend Developer (Responsible for converting data into a graphical interface) | 2 | 10000000 |  | 20000000
| SA | Implement Programs and Ensure fit to user needs | 1 | 10000000 |  | 10000000
| Testing | Software Tester to conduct tests to ensure the quality of the web-application | 1 | 3000000 |  | 3000000
[5 empty] | Grand Total | 198500000
Project Cost
Component | Detail | Description | Cost
Non-Technical | Electricity | Total Electricity Cost | 5000000
| Internet | Internet Cost | 2000000
Technical |  |  | 198500000
Server | 1 year domain |  | 500000
Others |  |  | 20600000
Profit |  |  | 67980000
| Total |  | 294580000