## Timeline and Human Resources
Project Web-Application OpenRead
LA06 |  |  | Human Resources
NIM | Name |  | PIC | Name
2201734814 | Anthony Gilrandy Theo |  | Project Manager (PM) | Steven
2201740546 | Dewi Puspita Tanurezal |  | Modelling (Designer) | Dewi
2201755131 | Devita |  | Software Analyst (SA) | Devita
2201852132 | Steven |  | Developer Backend (Dev BE) | Anthony
|  |  | Developer Frontend (Dev FE) | Devita
Steven
|  |  | Quality Assurance | Bu Sonya
TIMELINE
Task | Sub Task | PIC | September |  | October |  |  |  | November |  |  |  | December |  |  |  | January
|  |  | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
Requirement Engineering | Research | PM | bar: September 4 to October 1
| Questionnaire | PM | bar: October 1
| SRS | PM | bar: October 2 to October 3; November 2 to December 1
Analisis | Process Analayis | SA | bar: November 2 to November 3
| System's Diagram | SA | bar: November 2 to November 3
Modeling | User Interfaces | Designer | bar: November 3 to December 1
Backend Development | Initialize Project | Dev BE | bar: December 3
| Integration | Dev BE | bar: January 2
Frontend Development | Home Page | Dev FE | bar: December 3 to December 4
| Navigation Bar | Dev FE | bar: December 4
| Story Pages | Dev FE | bar: December 4 to January 1
| Profile Pages | Dev FE | bar: December 4 to January 1
Testing Integration | Testing | QA | bar: January 2

## Project Cost
Cost (Technical)
Component | Detail | Qty | Price |  | Subtotal
Hardware | Laptop | 4 | 10000000 |  | 40000000
Software | Project Manager | 1 | 100000000 |  | 100000000
| Designer | 1 | 5000000 |  | 5000000
| Backend | 1 | 20000000 |  | 20000000
| Frontend | 2 | 10000000 |  | 20000000
| SA | 1 | 10000000 |  | 10000000
| Testing | 1 | 3000000 |  | 3000000
|  |  |  | Grand Total | 198000000
Project Cost
Component | Detail | Cost
Non-Technical | Electricity | 5000000
| Internet | 2000000
Technical |  | 198000000
Server | 1 year domain | 500000
Others |  | 20550000
Profit |  | 67815000
| Total | 293865000