## Sheet1
Project Web-Application OpenRead
LA06 |  |  | Human Resources
NIM | Name |  | PIC | Name
2201734814 | Anthony Gilrandy Theo |  | Project Manager (PM) | Steven
2201740546 | Dewi Puspita Tanurezal |  | Modelling (Designer) | Dewi
2201755131 | Devita |  | Software Analyst (SA) | Devita
2201852132 | Steven |  | Developer Backend (Dev BE) | Anthony
|  |  | Developer Frontend (Dev FE) | Devita
Steven
|  |  | Quality Assurance | Bu Sonya
TIMELINE
Task | Sub Task | PIC | September |  | October |  |  |  | November |  |  |  | December |  |  |  | January
|  |  | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
Requirement Engineering | Research | PM | bar: September 4 to October 1
| Questionnaire | PM | bar: October 1
| SRS | PM | bar: October 2 to October 3; November 2 to December 1
Analisis | Process Analayis | SA | bar: November 2 to November 3
| System's Diagram | SA | bar: November 2 to November 3
Modeling | User Interfaces | Designer | bar: November 3 to December 1
Backend Development |  | Dev BE
Dev BE
Dev BE
Frontend Development |  | Dev FE | bar: December 3 to December 4
Dev FE
Dev FE
Dev FE
Testing Integration |  | QA